## 1. Product Overview
Item | Description
Product Name | SyncMeet-AI
Product Vision/ Purpose | SyncMeet-AI aims to enhance the quality and productivity of virtual meetings by providing real-time AI-driven monitoring, ensuring structured discussions, respectful communication, and automatic tracking of actionable outcomes.
Business Goals / Key Success factors | 1. Improve meeting efficiency and productivity 2. Reduce loss of actionable insights 3. Enable real-time discussion moderation 4. Automate task tracking and Agile tool updates 5. Ensure balanced participation among users 6. Achieve high accuracy in NLP-based detection (topic deviation, toxicity, action extraction)
Primary Stakeholders | 1. Students and educators (online classes, discussions) 2. Software development teams (Agile/Scrum meetings) 3. Project managers and team leads 4. Organizations conducting remote meetings 5. Developers integrating AI meeting tools

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Core Feature | US1 | As a user, I want real-time speech-to-text transcription, so that meeting conversations can be converted into text. | Python, SpeechRecognition / Whisper API, audio streaming | Must Have | 8 | To Do | Navaneeth S (Development Lead) | 1. Input audio → verify text output accuracy 2. Check latency < 2 sec | Rohith L (Test Lead)
E2 | Topic Deviation Detection | US2 | As a user, I want topic deviation detection, so that discussions stay on track. | Sentence-BERT, cosine similarity, NLP models | Must Have | 8 | To Do | Markandeshwaragouda Patil (Team Lead – core AI logic) | 1. Provide agenda + transcript 2. Verify deviation detection accuracy | Rohith L
E3 | Toxicity Detection | US3 | As a user, I want toxicity detection, so that communication remains respectful. | RoBERTa / HuggingFace toxicity model | Must Have | 5 | To Do | Nikhil M (Developer) | 1. Input toxic sentence → should flag 2. Normal sentence → should not flag | Rohith L
E4 | Action Item Extraction | US4 | As a user, I want action item extraction, so that tasks are captured. | NER, dependency parsing, LLM | Must Have | 8 | To Do | Markandeshwaragouda Patil | Input sentence → extract task, assignee, deadline | Rohith L
E5 | Meeting Summary Generation | US5 | As a user, I want meeting summary generation, so that I can review quickly. | Transformer summarization model (BART/T5) | Should Have | 5 | To Do | Nikhil M | 1. Input transcript → generate summary 2. Check key points coverage | Rohith L
E6 | Jira Integration | US6 | As a project manager, I want Jira integration, so that tasks are automatically created. | Jira REST API, authentication | Should Have | 8 | To Do | Pavan H K (DevOps) | Create task → verify in Jira | Rohith L
E7 | Dashboard (UI) | US7 | As a user, I want a dashboard, so that I can view insights. | Flask + HTML/CSS/JS | Must Have | 5 | To Do | Nikhil M | 1. UI loads correctly 2. Data displayed properly | Rohith L
E8 | Participation Analytics | US8 | As a user, I want participation analytics, so that I can see contribution levels. | Speaker tracking, data visualization | Could Have | 5 | To Do | Navaneeth S | Measure speaking time per user | Rohith L
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
The product development follows an iterative Agile approach, starting with a Minimum Viable Product (MVP) and progressively adding advanced AI features.
Release / Timeline | Focus Area | Key Features | Dependencies | Demo Status
Week 1–2 | Build a basic working pipeline (text input → AI processing → output) | 1. Text-based meeting input (manual transcript) 2. Basic topic deviation detection Basic toxicity detection 3. Simple UI (input + output display) | • Access to MSME business owners / auditors for interviews • GST portal documentation (GSTN official docs) • Survey tools (Google Forms / Typeform) • GitHub repo initialized (https://github.com/chetank23/GST-INVOICE-AI.git) • Team onboarding & role alignment | On Track
Week 3–4 | Integrate OCR engine to extract data from scanned invoices (PDF/images); validate extraction accuracy | OCR & Invoice Parsing Prototype | • OCR library: Tesseract OCR or Google Cloud Vision API (API key required) • PDF parsing library: PyMuPDF / pdfplumber • Sample invoice dataset (PDF, JPG, PNG formats) • Python environment with dependencies: pytesseract, Pillow, pdfplumber • Cloud storage (AWS S3 / Firebase) for uploaded invoices • Week 1–2 research outputs (invoice field definitions) | Planned
Week 5–6 | Build rule-based GST compliance validator; implement billing/invoice generation module; mismatch detection logic | GST Rule Engine + Billing System | • GSTN API access or GST rule documentation (CGST/IGST/SGST rate tables) • Week 3–4 OCR output as structured JSON input • Database setup (PostgreSQL / Firebase Firestore) for storing invoice records • Backend framework (Flask / FastAPI) with REST API endpoints • GST rate master data (HSN/SAC code list) • Payment gateway SDK (Razorpay / Stripe) for billing module • Authentication system (JWT tokens) — from Week 1–2 auth setup | Planned
Week 7–8 | Integrate WhatsApp API for invoice sharing & alerts; build analytics dashboard; end-to-end testing & QA | WhatsApp Billing Integration + Dashboard + Testing | • WhatsApp Business API (Meta Developer account + approved business number) • Twilio or 360dialog as WhatsApp messaging provider • Week 5–6 GST rule engine & billing APIs (must be stable) • Frontend framework (React.js / Flutter) for dashboard • Charting library (Chart.js / Recharts) for analytics widgets • End-to-end test suite (Pytest / Selenium) setup • CI/CD pipeline (GitHub Actions) for automated testing • UAT with at least 2–3 MSME customer contacts • Deployment environment (AWS EC2 / Heroku / Railway) | Planned

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead